## Sheet1
JIGAWA STATE DUE PROCESS AND PROJECT MONITORING BUREAU
PROCUREMENT PLAN FOR WORKS AND GOODS CONTRACTS
MINISTRY/ AGENCY: OFFICE OF THE STATE AUDITOR GENERAL, JIGAWA STATE
BUDGET YEAR: 2026
| PROJECT PARTICULARS |  |  |  | BASIC DATA |  |  | PROJECT PREPARATION |  |  |  | BIDDING PERIOD |  | BID EVALUATION & AWARD |  |  | CONTRACT MANAGEMENT & ADMINISTRATION |  |  |  | ANY OTHER REMARKS
| Project Description | Economic Code | Package No./File No. | Lot No. | Approved Threshold/ Budgeted Amount (Naira) | Estimated Amount in Naira | Procurement Method | Preparation & Submission of documents by MDAs | Post Review/ Vetting | Advert for Pre - Qualification | Pre-Qualification | Bid Invitation | Bid receipt and opening | Bid Evaluation & Report | Consideration of TEC Recommendation | Due Process Certificate of No Objection | Contract Approval & Offer | Contract Signing | Delivery/handover and acceptance | Final Payment
Date: Plan | Preocurement of 5no. Utility Vehicles for the State Audit Directorates | 014000100100 | AUD/PME/57A/I/2010/Vol. I | 1 | 110000000 | 110000000 | SELECTED | 2026-02-03 | 2026-02-16 | NIL | NIL | 2026-02-23 | 2026-03-09 | 2026-03-10 | 2026-03-20 | 2026-03-22 | 2026-03-25 | 2026-03-26 | 2026-04-16 | 2026-05-11 | First Quarter
Date: Actual
Cost (plan/actual)
Responsibility | [7 empty] | PROC. OFFICER | DPPMB | NIL | NIL | PROC. OFFICER | PROC. OFFICER | DTB | DTB | DPPMB |  | ALL PARTIES | PROJ. AUDIT DEPT. | ADMIN. & FINANCE | First Quarter
Date: Plan | Conduct a Research and produce a Performance Audit Report | 014000100100 | AUD/PME/57A/I/2010/Vol.1 | 2 | 20000000 | 20000000 | SELECTED | 2026-05-03 | 2026-05-16 | NIL | NIL | 2026-05-23 | 2026-06-09 | 2026-06-10 | 2026-06-20 | 2026-06-22 | 2026-06-25 | 2026-06-26 | 2026-06-28 | 2026-06-30 | Second Quarter
Date: Actual
Cost (plan/actual)
Responsibility | [7 empty] | PROC. OFFICER | DPPMB | NIL | NIL | PROC. OFFICER | PROC. OFFICER | DTB | DTB | DPPMB |  | ALL PARTIES | PROJ. AUDIT DEPT. | ADMIN. & FINANCE | Second Quarter
Date: Plan | Construction of New Hadejia Area Audit Office | 014000100100 | AUD/PME/57A/I/2010 | 3 | 120000000 | 120000000 | SELECTED | 2026-09-01 | 2026-09-08 | NIL | NIL | 2026-09-19 | 2026-09-22 | 2026-09-23 | 2026-09-25 | 2026-10-02 | 2026-10-03 | 2026-10-06 | 31/11/2026 | 2026-12-02 | Third Quarter
Date: Actual
Cost (plan/actual)
Responsibility | [7 empty] | PROC. OFFICER | DPPMB | NIL | NIL | PROC. OFFICER | PROC. OFFICER | DTB | DTB | DPPMB |  | ALL PARTIES | PROJ. AUDIT DEPT. | ADMIN. & FINANCE | Third Quarter
Date: Plan
Date: Actual
Cost (plan/actual)
Responsibility
w